OP NEBULAR - ASB and crime Sevenoaks Town Centre (Leisure centre/Environmental play park and Town car park)

OFFICIAL

Date & time: 19/05/2026 at 12:30 hours

Attendance:

- Charlotte Burns		Parking Services Manager - SDC

- Kelly Webb		Health & Communities Manager - Community Safety Unit - SDC

- Maxine Quinton 	Community Safety Officer - Community Safety Unit – SDC

- Shane Smith 		Leisure Centre Manager

- Georgina Jackson	Deputy Clerk - STC

- Nicholas Cave		Open Spaces and Cemetery Manager STC

- PS Edwards		Kent Police CSU Supervisor

- Residents x 4		Burlington Mews – Petra, David, Susie. Genette

- PCSO Darling		Kent Police CSU  - Child centred policing Team

- Michael Porter		Kent County Council-  Youth Outreach

- Charmaine Chapman	Kent County Council  - Youth Outreach

- Darren Mountain	House In The Basement -  Youth Worker

- Dennis Glasspool	Business Crime Reduction Partnership-  Lead

- Roberta Ware		Business Crime Reduction Partnership - Board

- PC Hubbard		Kent Police CSU Neighbourhood Task Force- Town officer

Apologies

- PC Harrison  		Kent Police CSU  - Child centred policing Team

- Sharon Wright		CCTV - SDC

- PS Cooke		Kent Police CSU Supervisor

- Insp Hinrich		Kent Police CSU Manager

- John Shanley		Kenward Trust

| ACTIONS |  | EVA = Environmental Visual Audit PMP = Proactive Management Plan MCV = My Community Voice CSU – Community Safety Unit |  |
| --- | --- | --- | --- |
| Action No: |  | Action: |  | Owner: |  | Summary: | Progress |
| 1 |  | Create Operational Name for the Problem Profile |  | PC Hubbard |  | Create a dedicated operational name to ensure all activity and intelligence are linked effectively. | Complete |
| 2 |  | Create OP INFO on STORM ( Flags OIC for Relevant Postcodes) |  | PC Hubbard |  | Ensure all incidents linked to hotspot postcodes are automatically flagged to CSU for review. | Complete |
| 3 |  | Communication with Local Schools |  | PC Harrison and PCSO Darling |  | Engagement with schools regarding ASB at this hotspot location. | Complete |
| 4 |  | Add Nominals to PMP and Monitor ASB Offenders |  | PC Harrison and PCSO Darling and PC Hubbard |  | Review cads within the scanning phase and identify repeat youths and add them as suspects to PMP 4269/26. | Ongoing |
| 5 |  | Encourage Early Reporting by Leisure Centre Staff |  | Shane SMITH |  | Shane to disseminate issue to staff and promote use of Shop Safe Radio and prompt reporting via 999/101 or online. | Complete |
| 6 |  | Community Engagement Group for Burlington Mews Residents |  | PC Hubbard |  | Create MCV/community messaging group for updates and intelligence sharing. | Complete |
| 7 |  | Conduct Resident and Partner Meetings and Online Forums |  | PC Hubbard |  | Regular meetings to review concerns, progress and gather feedback. | Complete |
| 8 |  | Centralised ASB Reporting |  | PC Hubbard |  | Review reporting system to simplify reporting pathways and ensure everything relating to OP NEBULAR is reported to the police. |  |
| 9 |  | Encourage Retention of CCTV and Mobile Phone Footage |  | Burlington Mews Residents |  | Residents encouraged to preserve evidence for police to review. This to be mentioned when reporting. |  |
| 10 |  | Increase Patrols During Peak Times |  | PC Hubbard/ INSP Hinrich |  | Implement hotspot patrol plans during evenings, weekends and school holidays. | Complete |
| 11 |  | CCTV Monitoring During Peak Times |  | Sharon Wright |  | Direct CCTV operators to hotspot locations during key periods. | Complete |
| 12 |  | Area Cleaning and Rapid Removal of Damage/Graffiti |  | Kelly Webb/Maxine Quinton |  | Ensure clean up following incidents to prevent general environmental degradation and smashed window effect. | Complete |
| 13 |  | Remove Shopping Trolleys and Broken Glass Promptly |  | Waitrose / M&S Den Glasspool |  | Prevent items being used in offending and improve environmental quality similar to above. | Complete |
| 14 |  | Conduct Full Environmental Visual Audit (EVA) |  | PC Hubbard |  | Review all hotspot locations for environmental vulnerabilities. |  |
| 15 |  | Enhance Signage Around Hotspot Areas |  | Kelly Webb / Maxine Quinton / PC Hubbard |  | Install signage relating to ASB enforcement and patrol activity. |  |
| 16 |  | Review Lighting Across Hotspot Areas |  | Kelly Webb / Maxine Quinton/ Linda Larter/ Georgina Jackson |  | Following EVA report - Upgrade lighting to improve visibility and natural surveillance across Locations. |  |
| 17 |  | Environmental Design Review of Trees, Bushes and Hiding Areas |  | Kelly Webb // Maxine Quinton/ Leisure Centre Manager |  | Following EVA report - Reduce concealed areas facilitating congregation and offending. |  |
| 18 |  | Consider Removal of Benches Outside Leisure Centre |  | Kelly Webb / Leisure Centre Manager |  | Following EVA report - Assess whether seating contributes to persistent congregation |  |
| 19 |  | Consider Changes to Area Beneath Awning |  | Kelly Webb / Leisure Centre Manager |  | Following EVA report - Assess fencing or redesign options to prevent congregation. |  |
| 20 |  | Utilise ASB Act Powers and Sanctions |  | PC Hubbard / PC Harrison / PCSO Darling |  | Use warnings, contracts and ASB legislation where proportionate and updated offenders onto PMP. | Complete |
| 21 |  | Consider Issuing Section 59 Warnings |  | PC Hubbard / PC Costin / CCTV Team/ Council |  | Target vehicles linked to nuisance driving on var park and issue s 59. | Complete |
| 22 |  | Install Fencing and Gates to Environmental Park |  | Trevor Kennett. Charlotte Burns |  | Following EVA report - Review feasibility for fencing and padlocks to prevent access following EVA findings. |  |
| 23 |  | Install Netting on Top Level of Car Park |  | Trevor Kennett. Charlotte Burns |  | Following EVA - Review netting to prevent objects being thrown from height. |  |
| 24 |  | Consider ANPR or Barrier Systems at Car Park Entrances |  | Trevor Kennett. Charlotte Burns |  | Following EVA - Assess options to restrict vehicle access to car park. |  |
| 25 |  | Youth engagement |  | Darren Mountain Michael Porter Charmaine Chapman Andy Watson |  | Youth workers to attend locations during peak periods to engage. | Ongoing |
| 26 |  | Consider section 34 dispersal powers |  | INSP Hinrich/ PS Cooke and PS Edwards |  | Consider sections 34, 35, and 37 of the Anti‑social Behaviour, Crime and Policing Act 2014 allow police to authorise dispersal powers, requiring individuals involved in or likely to commit anti-social behaviour to leave an area for up to 48 hours, and permit the seizure of items linked to such behaviour. | Complete |
| 27 |  | Consider Public Spaces Protection Order (PSPO) |  | Kelly Webb / Maxine Quinton |  | Review proportionality and evidential threshold for implementation. |  |

Date & time: 03/07/2026 at 12:30 hours

Attendance:

- Linda Larter		Clerk – STC

- Kelly Webb		Health & Communities Manager - Community Safety Unit – SDC

- Stephen Cziraki		CCTV - SDC

- Residents x 1		Burlington Mews – John

- Dennis Glasspool	Business Crime Reduction Partnership-  Lead

- Roberta Ware		Business Crime Reduction Partnership - Board

- PC Hubbard		Kent Police CSU Neighbourhood Task Force- Town officer

- PC Owen		Kent Police CSU Neighbourhood Task Force- Town officer

Apologies

- PC Harrison  		Kent Police CSU  - Child centred policing Team

- Sharon Wright		CCTV - SDC

- PS Cooke		Kent Police CSU Supervisor

- Insp Hinrich		Kent Police CSU Manager

- John Shanley		Kenward Trust

- Charlotte Burns		Parking Services Manager - SDC

- Maxine Quinton 	Community Safety Officer - Community Safety Unit – SDC

- Shane Smith 		Leisure Centre Manager

- Georgina Jackson	Deputy Clerk – STC

- Nicholas Cave		Open Spaces and Cemetery Manager STC

- PS Edwards		Kent Police CSU Supervisor

- PCSO Darling		Kent Police CSU  - Child centred policing Team

- Michael Porter		Kent County Council-  Youth Outreach

- Charmaine Chapman	Kent County Council  - Youth Outreach

- Darren Mountain	House In The Basement -  Youth Worker

Meeting Notes

At the start of the meeting, Kent Police provided an overview of calls received between 19/05/2026 and 03/07/2026 relating to the problem solving area. During this period, a total of three CADs were recorded, all linked to Sevenoaks Town Car Park. Two incidents related to nuisance vehicles causing excessive noise, resulting in four warning letters being issued, whilst a further incident involved youths on the roof of the car park causing a noise nuisance. All incidents occurred during May and June 2026. Sevenoaks District Council also reported a complaint received on 19 June 2026 regarding youths using inappropriate language within the Environmental Park in the presence of young children and families using the facility.

The meeting then reviewed progress against the 28 actions contained within the Problem Solving Plan. The following points were discussed:

• Action 5 – ShopSafe Radio Usage – Sevenoaks leisure centre

Roberta Ware reported that the Leisure Centre has not been making regular use of the ShopSafe radio system. It was agreed that PC Hubbard would complete a follow up visit to the Leisure Centre to identify the current managers, ensure staff are aware of the ShopSafe and encourage more consistent use of the radios.

• Action 10 – Hotspot Tasking

Partner agencies were informed that Hotspot Tasking had been stood down following a four week deployment. It was noted that the resource could be reinstated if required. Given the anticipated increase in ASB during the school summer holidays, it was agreed that a request would be submitted to Inspector Hinrich seeking the reinstatement of Hotspot Tasking throughout the summer holiday period.

• Action 12 – Smashed Glass at Environmental Park

Linda Larter reported that smashed glass is being found within the Environmental Park on an almost daily basis. The locations are sporadic across the site, although the majority of glass is found within the actual children's play area, particularly on the soft safety matting and around the benches. Whilst no specific days or times have been identified, the issue is regular occurrence. Police requested contact details for the street cleansing team to allow officers to identify any patterns relating to when and where the glass is being discovered. This will support a longer term problem solving. Police also advised that an MCV message would be circulated to local residents encouraging them to report incidents relating to smashed glass aswell as the normal noise nuisance and sus activity within the park.

• Action 13 – Abandoned Shopping Trolleys

Roberta Ware reported that four shopping trolleys had been left near her shop for several days. She had already notified Waitrose of the issue. The group discussed making better use of the ShopSafe radio network to notify supermarkets when abandoned trolleys are identified so that they can be collected promptly. PC Hubbard agreed to follow up with Waitrose to ensure the reported trolleys are removed.

• Action 15 – Police Signage

Kelly Webb advised that police signs have now been produced and that a purchase order is currently being progressed through Sevenoaks District Council. Kelly further advised that a number of signs previously used during the Swanley Issues Project remain available and could potentially be utilised in the interim until new signage arrangements are finalised.

• Action 16 – Environmental Park Infrastructure

Linda Larter informed the group that there is currently no electricity supply within the Environmental Park. It was agreed that this should be taken into consideration when officers undertake the planned Environmental Visual Audit (EVA).

• Action 22 – Ownership of Environmental Park Assets

Linda Larter advised that responsibility for the fencing and gates within the Environmental Park rests with the Town Council. To ensure ownership and responsibilities are correctly identified prior to completion of the EVA, PC Hubbard requested a map showing land ownership boundaries and areas of responsibility across the park and surrounding land.

The meeting concluded with agreement that the respective agencies would continue progressing the outstanding actions and provide further updates at the next review meeting.